DEETECH GROUP

# Website Modernization
Development Plan

Implementation blueprint for Claude AI coding workflows

Current platform: WordPress  |  Target: Next.js + Node.js + PostgreSQL  |  Hosting: Existing VPS

| Project parameter | Decision |
| --- | --- |
| Development approach | Self-development with Claude / AI coding tools |
| Target schedule | 30 working days; allow 5–7 calendar weeks depending on weekly hours |
| CMS scope | Basic CMS for pages, services, brands, products, and blog |
| Deployment | Docker Compose on an existing VPS, behind Nginx with HTTPS |
| Python / Flask | Not included in MVP; add only when a concrete Python-specific feature is required |
| Primary goals | Generate B2B enquiries, present services clearly, showcase AnPreD and future brands, preserve SEO |

# 1. Project Overview

Rebuild https://www.deetechgroup.com/ from WordPress into a maintainable, SEO-friendly, responsive website with a purpose-built admin CMS. The website should position DeeTech Group as the umbrella business identity and provide a clear directory of its services, brands, and products.

## Business outcomes

Present DeeTech Group's IT services and business capabilities professionally.

Generate qualified enquiries through clear contact, quote, and demo calls to action.

Showcase AnPreD and InfraShield, while supporting additional brands or companies later.

Allow an administrator to update pages, services, products, brands, and blog posts without code changes.

Retain existing valuable URLs, search metadata, content, and inbound links wherever possible.

Deploy safely to the existing VPS with backups, monitoring, and a documented rollback path.

## Scope boundaries

| Included in MVP | Deferred until after launch |
| --- | --- |
| Home, About, Contact, Services, Products, Brands, Blog | Customer portal / customer accounts |
| Admin login and CRUD CMS | CRM, ticketing, and lead assignment integrations |
| Contact enquiry storage and email notification | Newsletter campaign platform |
| SEO fields, sitemap, redirects, basic analytics | AI writing and advanced analytics |
| Docker, Nginx, HTTPS, backups, monitoring | Flask microservice unless required by a defined feature |

# 2. Recommended Technology Architecture

| Layer | Technology | Responsibility |
| --- | --- | --- |
| Frontend / public website | Next.js, React, TypeScript | Server-rendered public pages, responsive UI, metadata, sitemap, blog |
| Admin CMS | Next.js, React, TypeScript | Admin screens and content editing workflows |
| Backend API | Node.js, Express, TypeScript | Content APIs, authentication, authorization, enquiry handling |
| Database | PostgreSQL | Pages, services, brands, products, posts, admin users, enquiries |
| Styling | Tailwind CSS | Design tokens, responsive layouts, reusable UI |
| Deployment | Docker Compose, Nginx | Container lifecycle, routing, TLS termination |
| Source control / CI | Git + GitHub or GitLab | Branches, reviews, automated checks, releases |
| Optional Python | Flask, later only | A separately justified Python-based capability |

## Architecture principles

Keep the first release to one web app, one API service, and one database.

Do not add Flask merely to use three technologies; extra services increase deployment and maintenance work.

Use one repository initially, with clear app and infrastructure folders.

Keep PostgreSQL private on the Docker network; do not expose its port to the public internet.

Keep secrets out of Git and out of client-side bundles.

Store uploaded media on persistent storage or a suitable object-storage service, not in a disposable container layer.

## Suggested repository structure

deetechgroup/
├── apps/
│   ├── web/                 # Next.js / React / TypeScript
│   └── api/                 # Node.js / Express / TypeScript
├── packages/
│   └── shared-types/        # Shared API types, if useful
├── database/
│   ├── migrations/
│   └── seeds/
├── infrastructure/
│   ├── docker/
│   ├── nginx/
│   └── deployment/
├── tests/
│   ├── integration/
│   └── end-to-end/
├── docker-compose.yml
├── .env.example
└── README.md

# 3. Site Map and Content Requirements

| Page / area | Requirements |
| --- | --- |
| Home | Clear value proposition; service summary; featured brands/products; proof points; prominent quote/demo/contact CTAs |
| About | Group overview, mission, capabilities, accurate company/brand relationships |
| Services | Service index and individual service pages, benefits, deliverables, enquiry CTA |
| Brands / Companies | Directory of brands and companies with relationship type and website links |
| AnPreD profile | Overview, InfraShield link, documentation link, demo/contact CTA; use accurate legal relationship wording |
| Products | Product descriptions, capabilities, status, website/docs/download links |
| Blog / Resources | Listing, article page, category or tags if needed, author and publish date |
| Contact | Contact details, validated enquiry form, privacy notice, successful submission confirmation |
| Admin CMS | Manage pages, services, brands, products, blog posts, media and SEO fields |

Legal wording note: use “subsidiary company” only if the ownership and legal structure supports it. If AnPreD is a product brand operated by the existing proprietorship, use wording such as “A product brand by DeeTech Group” or “Part of the DeeTech Group portfolio,” as factually appropriate.

# 4. CMS Data Model

| Table | Core fields / notes |
| --- | --- |
| admin_users | id, email, password_hash, role, is_active, created_at, updated_at |
| pages | id, title, slug, body/content, status, seo_title, seo_description, published_at, timestamps |
| services | id, title, slug, description, image_url, status, sort_order, timestamps |
| brands | id, name, slug, relationship_type, description, logo_url, website_url, status, sort_order |
| products | id, brand_id, name, slug, description, website_url, documentation_url, status |
| blog_posts | id, title, slug, body, author_id, featured_image, status, published_at, SEO fields |
| media | id, file_name, storage_path, mime_type, alt_text, created_at |
| contact_enquiries | id, name, email, company, subject, message, status, created_at |

Add unique constraints for slugs and appropriate foreign keys.

Use migrations checked into version control; do not rely on manual production schema changes.

Use publication states such as draft and published. Public APIs must return only published content.

Validate uploaded file type and size; generate safe storage names and preserve alt text.

Add basic pagination to blog and admin lists.

# 5. API Backlog

| Method | Endpoint | Purpose |
| --- | --- | --- |
| GET | /api/v1/pages/:slug | Read published page |
| GET | /api/v1/services | List published services |
| GET | /api/v1/brands | List published brands / companies |
| GET | /api/v1/products | List published products |
| GET | /api/v1/blog | List published posts; pagination |
| GET | /api/v1/blog/:slug | Read a published post |
| POST | /api/v1/enquiries | Validate and save a contact enquiry; notify by email |
| POST | /api/v1/admin/login | Authenticate administrator |
| POST/PATCH | /api/v1/admin/pages | Create or update pages; use an ID route for updates |
| POST/PATCH | /api/v1/admin/services | Create or update services |
| POST/PATCH | /api/v1/admin/brands | Create or update brands |
| POST/PATCH | /api/v1/admin/products | Create or update products |
| POST/PATCH | /api/v1/admin/blog | Create or update blog posts |

For production, define consistent REST conventions, request/response schemas, pagination, error codes, and API tests. Protect all admin write routes on the server; hiding controls in React is not authorization.

# 6. Thirty-Working-Day Implementation Plan

## Week 1 — Foundation and design

| Day | Task / deliverable | Effort |
| --- | --- | --- |
| 1 | Audit WordPress pages, URLs, media, blog content, plugins and SEO metadata; create content inventory. | 4–6 h |
| 2 | Finalize sitemap, content types, design references, brand colors and responsive design. | 4–6 h |
| 3 | Create repository, lint/type-check/test scripts, environment templates and local Docker setup. | 4–6 h |
| 4 | Build shared header, footer, navigation, typography, buttons and responsive layout. | 5–7 h |
| 5 | Build homepage sections and first responsive review. | 6–8 h |

## Week 2 — Public pages

| Day | Task / deliverable | Effort |
| --- | --- | --- |
| 6 | Build About, Contact and service listing pages. | 5–7 h |
| 7 | Build service detail template and quote/contact CTAs. | 4–6 h |
| 8 | Build brands/companies directory and AnPreD profile. | 4–6 h |
| 9 | Build product listing/detail templates and external product links. | 4–6 h |
| 10 | Build blog listing/article templates; add baseline metadata and accessibility fixes. | 5–7 h |

## Week 3 — API and database

| Day | Task / deliverable | Effort |
| --- | --- | --- |
| 11 | Design PostgreSQL schema and create repeatable migrations and seed data. | 4–6 h |
| 12 | Build Express API foundation, validation, error handling and health endpoint. | 5–7 h |
| 13 | Build public content endpoints for pages, services, brands, products and blog. | 5–7 h |
| 14 | Build contact enquiry endpoint, database persistence, spam controls and SMTP notification. | 5–7 h |
| 15 | Implement admin authentication, session/cookie handling, role checks and tests. | 6–8 h |

## Week 4 — CMS

| Day | Task / deliverable | Effort |
| --- | --- | --- |
| 16 | Build protected admin layout, navigation and dashboard. | 4–6 h |
| 17 | Build page editing: create, edit, draft, preview, publish and unpublish. | 5–7 h |
| 18 | Build CRUD workflows for services, brands and products. | 5–7 h |
| 19 | Build blog editor, featured image, author and publication date workflows. | 5–7 h |
| 20 | Build media upload and SEO fields; validate permissions and input handling. | 5–7 h |

## Week 5 — Migration and release candidate

| Day | Task / deliverable | Effort |
| --- | --- | --- |
| 21 | Migrate approved copy, images and content; review placeholder or outdated material. | 4–6 h |
| 22 | Map old WordPress URLs to new routes; create and test 301 redirects. | 3–5 h |
| 23 | Test content publishing, admin permissions, contact forms and email delivery. | 5–7 h |
| 24 | Run responsive, accessibility, performance, dependency and security checks. | 5–7 h |
| 25 | Test database/media backups, restoration and rollback procedure in staging. | 3–5 h |

## Week 6 — Production launch

| Day | Task / deliverable | Effort |
| --- | --- | --- |
| 26 | Prepare production images, Docker Compose, Nginx config and health checks. | 4–6 h |
| 27 | Configure DNS, HTTPS, firewall, secrets, persistent volumes and off-server backups. | 4–6 h |
| 28 | Configure repeatable deployment, logs, uptime checks and error alerts. | 4–6 h |
| 29 | Run final acceptance tests; take a full WordPress/database/files backup; approve cutover. | 4–6 h |
| 30 | Deploy, verify redirects and forms, monitor traffic and indexing, document handover. | 4–6 h |

# 7. Definition of Done

Feature works end-to-end in a local or staging environment.

Inputs are validated on the server and expected errors are handled.

Admin operations enforce server-side authentication and authorization.

Relevant unit, integration, or end-to-end tests are added and executed.

No secrets are committed; .env.example contains names and safe placeholders only.

README and deployment instructions are updated.

Code is reviewed and committed in a small, descriptive Git commit.

No claim that tests passed is made unless tests were actually run.

# 8. Security and Reliability Requirements

Use HTTPS in production; restrict SSH to trusted IPs where practical.

Keep PostgreSQL off public interfaces and restrict container network access.

Use strong admin passwords, secure session cookies, CSRF protection where applicable, login throttling and password reset safeguards.

Use parameterized SQL or a reputable ORM; validate every request with a schema validator.

Rate-limit public forms and add bot/spam controls; do not trust client-side validation.

Validate media file size and type, generate safe file names, and prevent executable uploads.

Use least privilege for OS users, database roles and application credentials.

Patch the operating system, Docker, runtime dependencies and application packages.

Back up database and uploaded media to a separate location; periodically test restoration.

Configure log rotation, health checks, uptime monitoring and error alerts; avoid logging passwords, tokens or sensitive form contents.

# 9. VPS Deployment and Cutover Plan

Inspect current VPS capacity, operating system, free disk, memory, CPU, open ports, and existing web services before choosing ports or changing Nginx.

Create a staging hostname and separate staging environment; do not experiment against the live WordPress installation.

Build versioned Docker images for the web and API services. Use a persistent PostgreSQL volume and persistent media storage.

Configure Nginx as the public reverse proxy for ports 80/443 and enable TLS. Keep app and database ports private.

Load production secrets through server-side environment configuration or a secrets mechanism; never include them in the repository or image.

Run migrations, initialize the first admin account securely, seed approved content, and run health and acceptance tests.

Take a full WordPress backup, including database, uploads, configuration, and current URL inventory. Confirm that the backup is usable.

At cutover, deploy the approved version, configure DNS or reverse-proxy routing, enable redirects, and test critical pages and forms.

Monitor application logs, HTTP errors, contact submissions, uptime, and search indexing. Keep the WordPress backup and rollback procedure available until the new site is stable.

## Docker Compose design notes

Services: nginx, web, api, db. Nginx may run on the host or in a container; choose one approach and document it.

Only Nginx should expose public HTTP/HTTPS ports. Do not publish PostgreSQL to the internet.

Use health checks and startup dependencies, but make the application tolerate database startup/reconnection issues.

Use restart policies, bounded log rotation, pinned image versions and a documented update process.

Back up the database and media separately from the VPS; a Docker volume alone is not a backup.

# 10. SEO and WordPress Migration

Inventory existing URLs before development; preserve paths where sensible.

Export and review WordPress pages, posts, categories, media, metadata and any useful structured data.

Create 301 redirects for all changed valuable URLs; avoid redirect chains and loops.

Implement unique title and meta description fields, canonical URLs, Open Graph metadata and XML sitemap.

Use meaningful image alt text, accessible heading structure, robots directives and sensible internal links.

Keep analytics/search console tracking if already configured; verify enquiry conversion events after launch.

Test key URLs, 404s, redirects, sitemap, robots.txt and indexing after cutover.

# 11. Effort and Cost Planning

| Item | Planning estimate |
| --- | --- |
| Implementation effort | Approximately 150–180 hours; depends on content readiness and revisions |
| Schedule | 5–7 calendar weeks at roughly 25–30 focused hours per week |
| Hosting | Use existing VPS if capacity and isolation are sufficient |
| Recurring expenses | Domain, VPS, SMTP/email service if paid, off-server backup storage |
| Budget note | These are planning assumptions, not a vendor quotation; exclude the value of your own time |

If only 10–15 hours per week are available, plan for a longer calendar timeline. Avoid adding a customer portal, CRM, newsletter campaigns, AI features, or Flask service to the MVP unless one is a launch-critical requirement.

# 12. How to Work with Claude

Use Claude as an iterative coding partner. Ask it to inspect the current repository before changing files. Work one task at a time, test the result, review the diff, and commit before starting the next task.

## Recommended workflow

Create the repository and commit the plan document.

Ask Claude to propose the initial repository structure and architecture; review before generating files.

Implement the project skeleton and run lint, type checks and a health check.

Implement one page or API feature per prompt using the backlog.

Run the relevant tests locally; ask Claude to fix failures based on actual output.

Review changes for security, unexpected scope expansion, secrets, and dependency changes.

Commit working milestones and update the backlog/README after each phase.

Deploy to staging before production and require manual approval for cutover.

## Reusable Claude implementation prompt

You are the senior engineer helping implement the DeeTech Group website described in this plan.

Before making changes:
1. Inspect the existing repository and report the relevant files and current architecture.
2. Identify assumptions, risks, and dependencies.
3. Propose a small implementation plan and acceptance criteria for the current task.

Project stack:
- Next.js, React and TypeScript for the public website and admin UI
- Node.js, Express and TypeScript for the backend API
- PostgreSQL for persistence
- Docker Compose and Nginx for deployment
- Flask is explicitly out of scope for the MVP unless I approve a specific use case.

Implementation rules:
- Follow existing conventions; avoid unnecessary rewrites and dependencies.
- Validate inputs server-side and enforce server-side authorization for all admin writes.
- Do not hardcode secrets or expose server environment variables to the browser.
- Use migrations, safe database queries, useful error handling and appropriate tests.
- Keep public content limited to published records.
- Update README and .env.example when configuration changes.
- Do not modify production configuration or perform a live cutover without explicit approval.
- Never state that tests passed unless you executed them and observed success.

After implementation, report:
- Files changed and why
- Commands/tests executed and actual results
- Security considerations
- Remaining issues and the next smallest task

Current task: [PASTE ONE BACKLOG TASK HERE]
Acceptance criteria: [PASTE THE EXPECTED OUTCOME HERE]

# 13. Launch Acceptance Checklist

☐ Public pages and navigation work on desktop and mobile.

☐ Brands directory displays AnPreD and supports future entries from CMS.

☐ Admin can create, edit, preview, publish and unpublish supported content.

☐ Contact submissions are stored and email notifications are delivered.

☐ Unauthenticated users cannot access protected admin operations.

☐ SEO metadata, sitemap, canonical URLs and redirects are verified.

☐ HTTPS, firewall rules, persistent storage, secrets and off-server backups are configured.

☐ Database and media restoration has been tested.

☐ No known critical security or functional defects remain.

☐ Production deployment, monitoring, and rollback instructions are documented.

# 14. Official Technical References

Next.js self-hosting: https://nextjs.org/docs/app/guides/self-hosting

Next.js metadata and SEO: https://nextjs.org/docs/app/getting-started/metadata-and-og-images

Express production best practices: https://expressjs.com/en/advanced/best-practice-security.html

Docker Compose documentation: https://docs.docker.com/compose/

PostgreSQL documentation: https://www.postgresql.org/docs/

Document status: Implementation plan / initial baseline. Revise the schedule after the WordPress content inventory and VPS capacity check. The plan is intended to be used as the project specification and task backlog for Claude-assisted development.